## Sprint
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week) | [6 empty] | Week #3 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 30 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21
|  |  |  | 2018-11-08 | 2018-11-09 | 2018-11-10 | 2018-11-11 | 2018-11-12 | 2018-11-13 | 2018-11-14 | 2018-11-15 | 2018-11-16 | 2018-11-17 | 2018-11-18 | 2018-11-19 | 2018-11-20 | 2018-11-21 | 2018-11-22 | 2018-11-23 | 2018-11-24 | 2018-11-25 | 2018-11-26 | 2018-11-27 | 2018-11-28
|  |  | 120 | 40 | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Remaining Hrs (Total)
| Expolring Greenfoot for development | Kavina | 9 | 2018-11-08: 9
| Exploring design patterns for the project | Mili | 9 | 2018-11-08: 9; 2018-11-09: 8; 2018-11-10: 6; 2018-11-11: 3; 2018-11-12: 0
| Expolring Greenfoot for development | Reeya | 9 | 2018-11-08: 9
| Exploring design patterns for the project | Tapan | 9 | 2018-11-08: 9
| Project Journal skeleton | Kavina | 1 | bar: 2018-11-08 to 2018-11-28
| Task Sheet skeleton | Mili | 1 | 2018-11-08: 1; 2018-11-09: 0
| Project Task Board | Reeya | 1 | bar: 2018-11-08 to 2018-11-28
| Updating Readme (project idea) | Tapan | 1 | bar: 2018-11-08 to 2018-11-28
Team:
Kavina | 10 hours / Week
Mili | 10 hours / Week
Reeya | 10 hours / Week
Tapan | 10 hours / Week
Total Available Hours During Sprint: | 120